## Slide 1
DEPARTMENT OF CSE, CSIT
COURSE NAME – ADAPTIVE Software Engineering
Course Code: 24CI3201
8 .AGILE ESTIMATION AND VELOCITY

## Slide 2: 1. ESTIMATION TECHNIQUES
Common Techniques:
Planning Poker Team members use cards (0,1,2,3,5,8…) to estimate stories collaboratively.
T-Shirt Sizing Tasks are sized as XS, S, M, L, XL based on complexity.
Wideband Delphi Experts estimate independently → discuss → re-estimate → reach consensus.
Three-Point Estimation Uses:
  Optimistic (O)
  Most Likely (M)
  Pessimistic (P) Final estimate = (O + 4M + P) / 6

## Slide 3: 2. AGILE ESTIMATION BASICS
Agile estimation is relative, not absolute.
Key Ideas:
Focus on effort, complexity, and uncertainty
Compare tasks instead of assigning exact hours
Encourages team discussion & collaboration
👉 Principle: “Estimate to understand, not to be perfect.”

## Slide 4: 3. STORY POINTS & PLANNING POKER
Story Points:
Measure relative effort
Based on:
  Complexity
  Risk
  Effort
Fibonacci Scale:
👉 1, 2, 3, 5, 8, 13, 21...
Planning Poker Steps:
Read user story
Discuss requirements
Each member selects a card
Reveal simultaneously
Discuss differences & re-vote

## Slide 5: 4. ESTIMATION VELOCITY CONCEPT
What is Velocity?
👉 Amount of work completed in a sprint (in story points)
Important Points:
Measures team capacity
NOT individual performance
Helps in future planning
👉 Example: If a team completes 30 story points, velocity = 30

## Slide 6: 5. VELOCITY CALCULATION
Formula:
👉 Velocity = Sum of completed story points in a sprint
Example:
Story | Points
Login | 5
Payment | 8
Dashboard | 13
Total velocity | 26
Average Velocity:
👉 (Sprint1 + Sprint2 + Sprint3) / 3

## Slide 7: 6. SPRINT PLANNING USING VELOCITY
Velocity helps decide how much work to take into a sprint.
Steps:
Check past velocity (e.g., 30 points)
Consider team availability
Select user stories from backlog
Ensure total points ≈ velocity
Finalize sprint backlog
👉 Example:
Velocity = 30
Select stories totaling ~30 points

## Slide 8: ✅ Final Summary
Estimation = Relative sizing
Story Points = Effort measurement
Velocity = Team output per sprint
Sprint Planning = Use velocity to commit work

## Slide 9: Web references
IEEE Computer Society – Software Engineering Resources https://www.computer.org/education/bodies-of-knowledge/software-engineering
NPTEL – Software Engineering Courses
https://nptel.ac.in/courses/106101061
Atlassian Agile Tutorial – Scrum, Kanban, User Stories https://www.atlassian.com/agile

## Slide 10: Topic questions
Product Backlog vs. Sprint Backlog and the Mechanics of Backlog Refinement?
Deep Dive into the Kano Model for Feature Prioritization?
Managing Estimation Biases and the Execution of Planning Poker?

## Slide 11
THANK YOU
Team – ADAPTIVE SOFTWARE ENGINEERING